## Backlog
# | Item | Status | Start Date | End Date | Who? | Notes
1 | Register naked | chua xong | 20/6/14 | 20/6/14 | Giap | mã hóa
birthday control bỏ birthday ko dùng nữa cho ngắn
password char[]
upload avatar: image + relative path -> demo đc upload kiểu file bất kì
2 | Login naked | chua xong | 20/6/14 | 20/6/2014 | Giap | mã hóa
password char[] - phụ
sử dụng cookie
validate: sql+ ui: chiều dài kí tự, ngày sinh có tồn tại
3 | Database + tạo bảng | xong | 20/6/2014 | 22/6_ 23/6 | Hai, Dung | tạo bảng, đổi file MusicNetwork.sql -> refresh.sql
4 | thu thập ảnh | chua xong | 24/6 | 24/6 | Hai | ảnh từ trang vk.com như các icon
5 | giao diện player | chua xong |  |  |  | dùng để mở file audio
tham khảo: http://tympanus.net/codrops/2012/12/04/responsive-touch-friendly-audio-player/
6 | Tạo ảnh giao diện | xong | 23/6 | 24/6 | Hai | Dựa trên trang VK.com - để trong folder resource/ImageUI
7 | Các công nghệ tìm hiểu | chua xong |  |  |  | Ajax - Load Posts, Websocket - Realtime app
8 | chuc nang post | xong | 24/6 | 24/6 _ 27/6 | Hai | post(), deletePost(), getPost()
getPost: self-post, friend-post, friend-paticipate-post(chưa làm vì khó)
demo Paging
9 | chuc nang like | chua xong |  |  |  | addLike(), deleteLike()
10 | upload giao dien | chua xong | 26/6 | 27/6 | Ha
11 | trang music giao dien | chua xong | 26/6 | ? | Ha
12 | kết bạn | chua xong | 26/6 | ? | Dung
13 | demo infinite load | xong | 26/6 | 28/6 | Hai
14 | chức năng chính + test | chua xong | 27/6 | 30/6 | Hai | ✓createPost
✓getPost: getFriendPost + getCommentOfAPost
✓addLike
✓deleteLike
✓addComment
✓getMyMusic
✓searchMusic (type: -artist, -title) tên bài hát, tên ca sĩ, tên của đứa đăng bài
upload audio - tạo cái tên cho file audio đấy
getPopularMusic( getCategory + getMusic)
addSongToMyMusic
Việc thêm bạn bè sẽ để lại. Dùng insert bạn bè vốn có trong database
15 | search song | chua xong | 2014-06-07 | 2014-06-07 | Hai
16 | drop & drag + upload file | chua xong | 2014-07-06 |  | Giap
abc.wav<br/>
add post ngay khi post upload thành công
17 | hoàn thiện trang post | chua xong |  |  |  | tương tự cho comment
ko load tất cả audio cùng 1 lúc
Mọi người "Tự" xem xét công việc có thể sẽ làm và bổ sung =))
Các note cần thêm ý kiến. Vì vậy cũng viết thêm ý kiến của mình vào nhé
Happy Fun Yourself !
Tham khảo API | [5 empty] | https://vk.com/pages?oid=-17680044&p=API_Method_Description
https://vk.com/pages?oid=-17680044&p=wall.post
https://vk.com/pages?oid=-17680044&p=Advanced_API_Methods

## References
Issue | Link
Table variable , Temporary Table
http://odetocode.com/articles/365.aspx
http://www.sqlviet.com/blog/bang-tam-va-bien-kieu-bang#more-4143
Pass data in Procedure
http://www.sommarskog.se/share_data.html#temptables
Java Google Json (Gson) - Java to Json and back
http://www.studytrails.com/java/json/java-google-json-parse-json-to-java.jsp
nhieu thu
http://sites.fastspring.com/zaneacademy/product/all
http://hmkcode.com/java-servlet-send-receive-json-using-jquery-ajax/
Paging SQL
http://social.technet.microsoft.com/wiki/contents/articles/23811.paging-a-query-with-sql-server.aspx
Random
http://blog.sqlauthority.com/2007/04/29/sql-server-random-number-generator-script-sql-query/
Mixing Inner Join + Outer Join
http://weblogs.sqlteam.com/jeffs/archive/2007/10/11/mixing-inner-outer-joins-sql.aspx
audio
stackoverflow.com/questions/4923136/why-doesnt-firefox-support-mp3-file-format-in-audio
https://developer.mozilla.org/en-US/docs/Web/Guide/HTML/Using_HTML5_audio_and_video
int primary key
https://www.simple-talk.com/sql/learn-sql-server/primary-key-primer-for-sql-server/
Jquery Template
https://github.com/BorisMoore/jsrender
http://www.sitepoint.com/10-javascript-jquery-templates-engines/
Time ago
http://timeago.yarp.com/
SQL Server Trigger
http://www.dotnet-tricks.com/Tutorial/sqlserver/OPUH170312-After-Trigger,-Instead-of-Trigger-Example.html
Bootstrap Modal
http://www.tutorialrepublic.com/twitter-bootstrap-tutorial/bootstrap-modals.php
http://www.sitepoint.com/understanding-bootstrap-modals/
Html Entities
| http://css-tricks.com/snippets/javascript/htmlentities-for-javascript/ | &lt; &gt;
Upload File Sevlet 3
http://hayageek.com/docs/jquery-upload-file.php#advanced
http://docs.oracle.com/javaee/6/tutorial/doc/glraq.html
http://docs.oracle.com/javaee/7/tutorial/doc/home.htm
Encode or Decode HTML entities with jQuery
http://www.naveen.com.au/javascript/jquery/encode-or-decode-html-entities-with-jquery/289
Log in remember
http://stackoverflow.com/questions/5082846/java-ee-6-how-to-implement-stay-logged-in-when-user-login-in-to-the-web-appli

## Sheet1
PostId | PostContent | PostTime | PostAccountId | LikePostCount | CommentId | CommentContent | CommentTime | CommentAccountId | LikeCommentCount

## Normalize
FriendId | Date type | Note
AccountId | int |  | Account
Password | varchar(30) |  | AccountId
Email | varchar(30) |  | Password
Name | nvarchar(30) |  | Email
Birthday | nvarchar(30) |  | Name
Phone | varchar(30) |  | Avatar
Gender | bit |  | Online
Avatar | date
Online | tinyint | 0 Off - 1 Online
PostId | int |  | Relationship |  | Artist | Category |  | SongId
PostTime | datetime |  | UserIdOne |  | ArtistId | CategoryId |  | SongId
PostContent | ntext |  | UserIdTwo |  | ArtistName | CagegoryName |  | Title
PostUser | int |  | RelationshipId
UserIdOne | int |  | status | 1_0
UserIdTwo | int
RelationshipId | int
LikeUser | int |  | Chat |  | MusicOwner | File
SongId | int identity |  |  |  | AccId | FileId
SongName | nvarchar(30) |  | ChatContent |  | FileId | FileName
AuthorId | int |  | ChatTime |  | CategoryId | ListenTimes
AuthorName | nvarchar(30) |  | RelationshipId |  | ArtistId
SongSinger | nvarchar(30) |  | ChatDirection |  | SongId
CategoryId | int
CategoryName | nvarchar(30)
ListenTimes | int
SelfId | int |  | Post |  | Comment |  | Like
FriendId | int |  | PostId |  | CommentId |  | LikeId
ChatContent | ntext |  | PostTime |  | CommentTime |  | LikePlaceId
ChatDirection | bit |  | PostContent |  | CommentContent |  | AccIdLike
chatTime | datetime |  | PostAcc |  | PostId |  | LikeType
CommentAcc