## Sprint1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a Admin, i want to create Course | Database | Chi, Ha, Truong | Done | 7 | 7 | 7 | 7 | 7 | 0
| Design Interface | Gideon, Daniel | Done | 3 | 3 | 3 | 3 | 3 | 0
| Code | Chi, Ha | In Progress | 3 | 3 | 2 | 1 | 1 | 2
| Test | Chi, Ha | In Progress
As a Admin, i want to assign to CL | Database | Chi, Ha, Truong | Done | 7 | 7 | 7 | 7 | 7 | 0
| Design Interface | Gideon, Daniel | Done | 3 | 3 | 3 | 3 | 3 | 0
| Code | Chi, Ha | In Progress | 3 | 3 | 2 | 1 | 1 | 2
| Test | Chi, Ha | In Progress
As a CL, I want assigned to a course for 1 year | Database | Chi, Ha, Truong | Done | 7 | 7 | 7 | 7 | 7 | 0
| Design Interface | Giap | Done | 2 | 2 | 2 | 2 | 2 | 1
| Code | Chi, Giáp | In Progress | 3 | 3 | 2 | 1 | 1 | 2
| Test | Chi, Giáp | In Progress
As a User member, I want to login to the page | Database | Chi, Ha, Truong | Done | 7 | 7 | 7 | 7 | 7 | 0
| Design Interface | Daniel | Done | 3 | 3 | 3 | 3 | 3 | 0
| Code | Chi, Giáp | In Progress | 3 | 3 | 2 | 1 | 1 | 2
| Test | Chi, Giáp | In Progress
Sprint Goal
Some sprint goal
Link
https://docs.google.com/spreadsheets/d/151N-IJiSzJO6OrwYm_Fmqwm4BST8RixKbJs0XNB-DHo/edit#gid=0

## Sprint 2
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a CL, I want to create CMR for course that assigned to me | Database | Chi, Ha, Truong | Done | 7 | 7 | 7 | 7 | 7 | 0
| Design Interface | Gideon, Daniel | Done | 3 | 3 | 3 | 3 | 3 | 0
| Code | Chi, Ha | In Progress | 3 | 3 | 2 | 1 | 1 | 2
| Test | Chi, Ha | In Progress
As aCL, I want to send CMR to CM to approve by email | Database | Chi, Ha, Truong | Done | 7 | 7 | 7 | 7 | 7 | 0
| Design Interface | Gideon, Daniel | Done | 3 | 3 | 3 | 3 | 3 | 0
| Code | Chi, Ha | In Progress | 3 | 3 | 2 | 1 | 1 | 2
| Test | Chi, Ha | In Progress
As a CL, I want to send approved CMRs to DLT | Database | Chi, Ha, Truong | Done | 7 | 7 | 7 | 7 | 7 | 0
| Design Interface | Giap | Done | 2 | 2 | 2 | 2 | 2 | 1
| Code | Chi, Giáp | In Progress | 3 | 3 | 2 | 1 | 1 | 2
| Test | Chi, Giáp | In Progress
Sprint Goal
Some sprint goal

## Sprint 3
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation | Task 1 | Michael | Closed | 7 | 7 | 0 | 0 | 0 | 0
| Task 2 | Ben | Closed | 3 | 3 | 3 | 0.5 | 0.5 | 0
| Task 3 | Ben | In Progress | 3 | 3 | 2 | 1 | 1 | 2
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 1 | Michael | Closed | 1 | 1 | 1 | 1 | 1 | 0
| Task 2 | Andrew | Closed | 0 | 0 | 7 | 0 | 0 | 0
| Task 3 | Andrew | Closed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Task 4 | Andrew | Closed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Total |  |  | 15 | 15 | 14 | 3.5 | 3.5 | 2
Sprint Goal
Some sprint goal

## Group 3
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation | Task 1 | Michael | Closed | 7 | 7 | 0 | 0 | 0 | 0
| Task 2 | Ben | Closed | 3 | 3 | 3 | 0.5 | 0.5 | 0
| Task 3 | Ben | In Progress | 3 | 3 | 2 | 1 | 1 | 2
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 1 | Michael | Closed | 1 | 1 | 1 | 1 | 1 | 0
| Task 2 | Andrew | Closed | 0 | 0 | 7 | 0 | 0 | 0
| Task 3 | Andrew | Closed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Task 4 | Andrew | Closed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Total |  |  | 15 | 15 | 14 | 3.5 | 3.5 | 2
Sprint Goal
Some sprint goal

## Sheet4
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
As a / an website visitor I want to view a home page so that I can see the most important content at a glance and quickly understand the site navigation | Task 1 | Michael | Closed | 7 | 7 | 0 | 0 | 0 | 0
| Task 2 | Ben | Closed | 3 | 3 | 3 | 0.5 | 0.5 | 0
| Task 3 | Ben | In Progress | 3 | 3 | 2 | 1 | 1 | 2
As a / an website visitor I want to be able to log in to the site so that I can see tailored content and manage my relationship with the company | Task 1 | Michael | Closed | 1 | 1 | 1 | 1 | 1 | 0
| Task 2 | Andrew | Closed | 0 | 0 | 7 | 0 | 0 | 0
| Task 3 | Andrew | Closed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Task 4 | Andrew | Closed | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Total |  |  | 15 | 15 | 14 | 3.5 | 3.5 | 2
Sprint Goal
Some sprint goal